## Detailed Scrum Log
Day | Product Owner Work | Scrum Master Work | Developer Work | Client Work
Day 1 | Held project kickoff. Presented the vision of WebMsh: a browser-based mesh generation platform built on the Gmsh Python API. Defined V1 scope and success criteria for the single 3-week sprint. | Introduced Scrum in single-sprint mode: daily standups, a shared backlog, and a sprint review at week 3. Created the sprint board with all user stories and effort estimates. | Installed Gmsh locally and ran Python API test scripts. Explored OCC primitives and verified mesh generation end-to-end. Began researching Three.js for browser rendering. | Attended kickoff. Described key use cases: FEA pre-processing, CFD meshing, and STL export for 3D printing. Requested simple browser access with no software installation required.
Day 2 | Drafted the full product backlog in one session. Wrote user stories for geometry creation, boolean operations, mesh generation, physical group assignment, and multi-format export. Prioritised MVP. | Facilitated backlog refinement. Split large stories into daily-sized tasks. Highlighted risk: Gmsh is not thread-safe and requires one process per user session. | Researched Three.js OrbitControls and BufferGeometry for 3D surface display. Identified raycasting for click-to-select. Designed the overall system architecture: FastAPI + per-user Gmsh process + React frontend. | Reviewed draft backlog. Prioritised visual 3D inspection and mesh export as top priorities. Requested that STEP and STL import be included from the start.
Day 3 | Locked V1 feature set: 5 OCC primitives, 3 boolean ops, mesh 1D/2D/3D, physical groups, 6 export formats, interactive 3D viewer. Deferred boundary layers and parametric models. | Documented key risks: large mesh transfer overhead, browser memory limits, OCC boolean fragility. Approved mitigation strategies (streaming, session caps, 422 error surfaces). | Began writing the SRS document. Completed Section 1 (Introduction, Purpose, Scope, Definitions) and Section 2 (Business Requirements, User Needs, Constraints, Assumptions). | Read SRS draft sections 1-2. Confirmed user needs table matches real workflows. Requested that physical group colour-coding be explicitly included in the viewer requirements.
Day 4 | Reviewed SRS progress. Confirmed API contract conventions: JSON for metadata, binary buffers for mesh and geometry data, JWT Bearer token auth for all non-auth routes. | Ensured architecture decisions were documented. Clarified that auto-save is out of scope for this sprint — manual save (Ctrl+S) only. Updated sprint board accordingly. | Completed SRS Section 3: all feature tables (geometry, boolean ops, transforms, mesh, physical groups, export, viewer, UX workflow), all functional requirements, external interface requirements, and non-functional requirements. SRS document finalised. | Reviewed complete SRS. Approved all feature requirements. Noted the 50 MB file upload cap and 100 req/min rate limit as constraints to validate during testing.
Day 5 | Signed off on the SRS document. Confirmed the sprint is on track. Clarified expected UI layout: left collapsible sidebar, central 3D viewport occupying at least 60% width, top toolbar. | Ran daily standup. Confirmed no blockers. Noted that OAuth is deferred — sign-in will use a simple name entry and optional Bearer token paste to avoid blocking frontend progress. | Initialised the frontend project: Vite 5, React 18, React Router 6, Three.js 0.165. Created package.json, vite.config.js with /api and /ws proxy rules to port 8000, and index.html entry point. | Saw the initial app scaffold running at localhost:5173. Confirmed dark theme preference and requested the viewport background use a dark neutral tone.
Day 6 | Confirmed backend API endpoint naming: /projects, /geometry/*, /mesh/*, /physical-groups/*, /export/*. Approved undo/redo via POST /undo and /redo with snapshot-based state restore. | Resolved naming ambiguity between project-level save and per-operation auto-save. Removed auto-save from scope. Updated sprint board. Ensured all developers were unblocked. | Built the full API client (api.js): project CRUD, geometry creation and transforms, boolean operations, file import, mesh generate/stats/export, physical groups, undo/redo. Built AppContext providing global state — entities, selection, tessellation, toasts — to all components. | Reviewed the API endpoint list. Asked about error response format — confirmed HTTP 422 with descriptive message for geometry and mesh failures, surfaced as toast notifications.
Day 7 | Updated sprint board to reflect completed tasks. Added new ticket for keyboard shortcuts (Ctrl+S, Ctrl+Z, Ctrl+Y, Delete, Escape) after developer flagged them as essential UX. | Tracked daily standup. No blockers. Confirmed that PrivateRoute must redirect to / (sign-in) on missing token, not a 404 — developer confirmed the fix was already in place. | Built SignIn.jsx (name entry + optional Bearer token, no OAuth dependency), Dashboard.jsx (project cards with create, rename, delete, last-modified timestamp), Toast.jsx, and the full dark-theme global CSS: design tokens, button/input/form utilities, all page layouts. | Tested sign-in with a dev token. Confirmed project card layout is clear. Requested that rename and delete require only one click without nested menus.
Day 8 | Reviewed dashboard completion. Confirmed project open flow: POST /open then navigate to /editor/:id. Approved the sidebar tab structure: Geometry, Mesh, Groups, Tree. | Facilitated standup. Confirmed that the export dropdown in the toolbar and the export strip pinned to the sidebar bottom are both needed per SRS — not duplicates. | Built Editor.jsx (loads project state on mount, Ctrl+S/Z/Y keyboard shortcuts wired), Toolbar.jsx (Save, Undo, Redo, Export format dropdown for all 6 formats), and Sidebar.jsx (four tabs: Geometry, Mesh, Groups, Tree; collapsible via toggle button; Export strip at bottom). | Reviewed editor layout in browser. Approved the collapsible sidebar. Confirmed that the viewport fills remaining space correctly via CSS flex. No change requests.
Day 9 | Approved editor shell and sidebar structure. Shifted focus to the Three.js viewer — highest complexity remaining item. Confirmed camera auto-fit and click-to-select are both required. | Monitored velocity. Flagged that the viewer must perform well with medium-sized meshes (hundreds of thousands of triangles). Noted as a stretch goal to reduce draw calls using merged geometry. | Built Viewer3D.jsx: Three.js WebGL renderer with antialiasing, PerspectiveCamera, AmbientLight and DirectionalLight, GridHelper, AxesHelper, OrbitControls with damping, ResizeObserver for canvas resize, raycasting on click for entity selection, tessellation geometry rebuild when data changes, camera auto-fit to bounding box on load, orange selection highlight, mesh stats overlay, and reset-view button. | Saw the Three.js scene running with orbit, pan, and zoom. Confirmed controls feel responsive. Requested geometry be rendered in blue-grey rather than white, and that unselected edges be dark.
Day 10 | Confirmed viewer implementation meets SRS requirements: shaded surface, edge overlay, click-to-select, axis gizmo, hover highlight via raycasting. Approved proceeding to feature panels. | Ran daily standup. Raised that boolean operations in the sidebar need a guard (minimum 2 entities selected) and descriptive helper text — added to upcoming GeometryPanel ticket. | Built GeometryPanel.jsx: collapsible detail sections for all five OCC primitives (Box, Sphere, Cylinder, Cone, Torus) with validated numeric input forms and API calls that update entity list and tessellation on success. Each section shows the relevant Gmsh API call for reference. | Tested the Box and Sphere creation forms. Confirmed inputs are intuitive. Asked whether forms reset after submission — confirmed values persist to allow quick repeat creation with minor edits.
Day 11 | Reviewed geometry panel primitives completion. Confirmed boolean UX: first half of selected entities are objects, second half are tools for Fuse/Intersect; first entity is object, rest are tools for Cut. | Removed blocker: clarified that the file import endpoint uses multipart/form-data, not JSON. Confirmed the api.js upload() function omits Content-Type so the browser sets the correct boundary. | Extended GeometryPanel.jsx with: Boolean Operations (Fuse, Cut, Intersect — disabled until 2+ entities selected, selection count shown inline), Transform sections (Translate with dx/dy/dz, Rotate with origin+axis+angle, Scale with origin+factor), Copy selected, Delete selected, and STEP/STL file import via file picker. | Tested boolean cut by selecting two boxes. Confirmed the operation triggered correctly. Requested that OCC failure messages (e.g. tangent face errors) appear as error toasts — confirmed already handled via 422 response.
Day 12 | Confirmed mesh panel requirements in detail: global min/max element size, 2D algorithm selector (MeshAdapt, Delaunay, Frontal-Delaunay, BAMG), 3D algorithm selector (Delaunay, Frontal, HXT), recombine and second-order toggles, mesh stats, optimize and refine buttons. | Tracked standup. Noted mesh generation can be long-running — confirmed the frontend shows a spinner on generate buttons and the backend handles progress via WebSocket (out of frontend scope). | Built MeshPanel.jsx: mesh settings form (min/max size, 2D and 3D algorithm selects, recombine and second-order checkboxes), 1D/2D/3D generate buttons each posting current settings, mesh stats section (node count, element counts by type, min/max element size), and optimize/refine buttons (Netgen, Laplace, uniform refine). | Generated a 3D mesh on a test box geometry. Statistics displayed correctly. Asked whether mesh overlay in the viewer differs from geometry surface — logged as a potential viewer enhancement for a future sprint.
Day 13 | Confirmed physical group requirements: create per dimension (0D-3D), assign name, add entities via click-to-select in viewer, auto colour-code up to 12 groups distinctly, persist with project save. | Ensured ModelTree and PhysicalGroupsPanel both read from AppContext exclusively — no local entity copies — to keep selection state consistent between viewer, tree, and group panel. | Built PhysicalGroupsPanel.jsx: create group with name and dimension selector, add or remove selected entities, display colour swatch from a 12-colour palette, delete group with confirmation. Built ModelTree.jsx: entities listed by dimension (Points, Curves, Surfaces, Volumes), each row clickable to toggle selection, synced with viewer orange highlight. | Tested physical group creation and entity assignment. Liked the colour swatch display. Asked whether groups are preserved after mesh generation — confirmed yes, as physical groups are independent of mesh state in Gmsh.
Day 14 | Reviewed all panels complete. Confirmed full user journey works end-to-end in the UI: sign in, create project, create geometry, boolean ops, set mesh settings, generate mesh, assign physical groups, export. | Facilitated pre-review standup. Ran through open issues: export dropdown z-index overlap when sidebar is narrow, missing loading state on project open. Both assigned to developer for same-day fix. | Fixed export dropdown z-index issue in narrow sidebar. Added loading spinner to project open in Dashboard. Fixed Toolbar export dropdown to dismiss on outside-click using a blur handler. Ran full regression check across all sidebar panels using browser devtools network panel to verify API calls and payloads. | Retested all three reported issues — confirmed resolved. Performed independent walkthrough of the complete flow. Found no new issues. Confirmed file picker correctly restricts to .step, .stp, .stl extensions.
Day 15 | Conducted sprint review. Walked through SRS Section 3.1 feature checklist line by line against the implemented frontend. Confirmed every V1 in-scope feature has a corresponding component. Signed off sprint as complete. | Facilitated final sprint retrospective. Ran npm run build — production build succeeded: Vite 5, 49 modules, 0 errors, 672 kB JS bundle (182 kB gzip), 7.6 kB CSS, build time 3.64s. Noted Three.js chunk size advisory as a future code-splitting task. Closed all sprint board items. | Wrote frontend README covering prerequisites (Node 18+), install (npm install), dev server (npm run dev), production build (npm run build), and environment config for backend URL. Added code comments to Viewer3D.jsx and api.js. Demonstrated complete working system: dashboard, 3D viewer, all geometry and mesh panels, physical groups, model tree, export to 6 formats, undo/redo, and all keyboard shortcuts. | Attended sprint review demo. Confirmed all originally requested features are present and working. Approved the frontend MVP deliverable. Noted OAuth sign-in and auto-save as prioritised items for the next sprint.